## Team Info
Team Name
Students
Name | ID | Email | Tutorial
Roger Elias | 58-0352 | roger.elias@student.guc.edu.eg | 25
Monica Mina | 58-4467 | monica.samaan@student.guc.edu.eg | 15
Rodaina elsawy | 58-16542 | rodaina.elsawy@student.guc.edu.eg | 27
Maria Awad | 58-5927 | maria.awad@student.guc.edu.eg | 17
Ali Ahmed | 58-3693 | ali.aboelkher@student.guc.edu.eg | 28

## Milestone1.2
Module | Depends on User Story ID | Requirement ID | User Story |  |  | Notes
|  |  | As a | I want to | So that
Profile and Identity | - | 1 | Company | Apply for a profile | I can get scad approval to post Internship Jobs |  | Students | Profile and Identity Module
Profile and Identity | - | 2 | Student | Login to my profile | I can browse and view available Internships |  | Companies | Internship Search and Recruitment Module
Profile and Identity | 2 | 3 | Student | Upload my CV/ Photo | I can start applying for available internships |  | SCAD Office | Evaluation and Reporting Module
Profile and Identity | 2 | 4 | Student | Add my Certifications to my profile | I can showcase my knowledge
Profile and Identity | 2 | 5 | Student | Add my skills | I can be matched with internship opportunities | each student profile will have a skills section
Profile and Identity | 1 | 6 | SCAD | View Company profile applications | I can grant them access to post internships |  | Faculty Academics
Profile and Identity | 2025-01-06 | 7 | Company | Receive notification that my profile got approved | I can start posting about job opportunities
Internship Search and Recruitment |  | 8 | Faculty Academic | Login to my profile | I can create and manage internal Internship Jobs for research projects
Internship Search and Recruitment |  | 9 | Company/Faculty Academic | Publish Internship opportunities | I can find qualified students
Internship Search and Recruitment | 9 | 10 | Company/Faculty Academic | Specify the duration & pay of the Internship | Send the Internship post for approval
Internship Search and Recruitment | 2025-09-10 | 11 | SCAD | review companies’ internship posts | I can ensure they comply with University guidelines | Internship posts must be submitted by Company/Faculty Academic (Reqs 9 & 10)
Internship Search and Recruitment | 2010-02-09 | 12 | Student | navigate job announcements in a user-friendly interface | I can quickly find a suitable opportunity | Requires student login (Req 2) and approved internship posts (Reqs 9 & 10)
Internship Search and Recruitment | 2010-02-09 | 13 | Student | filter announcements based on my preferences | I can efficiently find internship opportunities that match my interests | Requires student login (Req 2) and approved internship posts (Reqs 9 & 10)
Internship Search and Recruitment | 2010-02-09 | 14 | Student | click on a job posting announcement | I can view the full job description | Announcement must include the internship title and company name; requires student login (Req 2) and approved internship posts (Reqs 9 & 10)
Internship Search and Recruitment | 2, 5, 9, 10 | 15 | Student | see a percentage match between my skills and the job requirements | I can quickly determine if the job is a good fit for me | Requires student login (Req 2), student skills added (Req 5), and approved internship posts (Reqs 9 & 10)
Internship Search and Recruitment | 2025-02-14 | 16 | Student | view detailed job information | I can learn more about the job and decide whether to apply | Requires that the job posting announcement has been clicked (Req 14) and student login (Req 2)
Internship Search and Recruitment | 2025-02-16 | 17 | Student | contact company recruiters regarding a specific job post | I can clarify any questions I have about the job before applying | Depends on detailed job information being available (Req 16) and student login (Req 2)
Internship Search and Recruitment | 2016-02-03 | 18 | Student | apply for a job | I can be considered for the position | Requires detailed job information (Req 16), student login (Req 2), and CV/photo uploaded (Req 3)
Internship Search and Recruitment | 2025-02-14 | 19 | Student | share a job announcement with other students | I can help my peers discover new opportunities | Requires the job posting announcement to be visible (Req 14) and student login (Req 2)
Internship Search and Recruitment | 2025-02-14 | 20 | Student | follow a company | I can customize my job announcement feed and stay updated on their opportunities | Requires the job posting announcement to include company information (Req 14) and student login (Req 2)
Internship Search and Recruitment | 19 | 21 | Student | Turn on email notifications for a company | I can apply early before spots fill up | notifications in the form of Emails
Internship Search and Recruitment | 2025-09-18 | 22 | Company/Faculty Academic | Recieve notifications when students apply | I can secure top candidates | daily/weekly emails with the number of new applicants per job post
Internship Search and Recruitment |  | 23 | Student | Save and organize internship postings | I can compare and prioritize opportunities
Internship Search and Recruitment | 2025-09-18 | 24 | Company | View applied candidates' profiles | I can shortlist the best matches
Internship Search and Recruitment | 18 | 25 | Company/Faculty Academic | Select Potential Candidates | I can advance them to the next stage
Internship Search and Recruitment | 25 | 26 | Company/Faculty Academic | Schedule Interviews | I can properly evaluate candidates
Internship Search and Recruitment | 26 | 27 | Student | Receive interview notifications | I can prepare and attend on time
Internship Search and Recruitment |  | 28 | Student | Track my application status | I know where I stand and can take action if needed
Internship Search and Recruitment |  | 29 | Company/Faculty Academic | Send acceptance notifications | Candidates can confirm quickly and I can finalize my selections
Internship Search and Recruitment | 24 | 30 | Company/Faculty Academic | Send rejection notifications | Candidates can move on and apply for other opportunities
Internship Search and Recruitment | 24 | 31 | Student | confirm my acceptance of the internship offer | I can officially begin my internship and complete my graduation requirement
Internship Search and Recruitment | 29 | 32 | Company | Download an applicant's CV | I can share it with my recruitment team for review
Internship Search and Recruitment |  | 33 | Company | view anonymized feedback from past internship evaluations of a student | I can assess their prior performance while maintaining confidentiality
Internship Search and Recruitment |  | 34 | Student | receive real-time notifications regarding the status of my internship application | I can track whether I am accepted, rejected, or still under review
Evaluation and Reporting |  | 35 | Company/Faculty Academic | complete the SCAD evaluation form | I can assess the intern's performance based on multiple metrics and dimensions
Evaluation and Reporting |  | 36 | Student | submit free-form feedback about my internship experience | I can share insights about the company and the role I undertook
Evaluation and Reporting |  | 37 | SCAD | define and provide a standardized internship report template with required questions | students provide all necessary information for their internship to be considered complete
Evaluation and Reporting |  | 38 | Student | write a review about my internship company | uture interns can make informed decisions when applying
Evaluation and Reporting | 38 | 39 | Student | submit my completed internship report | the SCAD office can evaluate my internship and determine whether it meets the graduation requirements
Evaluation and Reporting | 39 | 40 | SCAD | review and approve submitted internship reports | I can ensure they meet the university’s academic and quality standards
Evaluation and Reporting | 39 | 41 | SCAD | Specify Internship submission deadlines | the system can notify students on time and ensure timely report submissions
Evaluation and Reporting | 2025-09-18 | 42 | Company | View internship metrics (number of applicants ,acceptance rate) | I can analyze recruitment performance and optimize our hiring process
Evaluation and Reporting | 9,10, 29, 31 | 43 | Company/Faculty Academic | Grant certification to students upon completion | Students have official proof of their experience
Evaluation and Reporting | 6 | 44 | Student | Report suspicious companies | SCAD can review and remove fraudulent announcements, ensuring a safer internship experience
Evaluation and Reporting | 35 | 45 | Student | View the company evaluation | I can understand my performance during the internship and identify areas for improvement
Evaluation and Reporting | 31 | 46 | Student | Write a post about my internship experience | I can showcase my achievements and attract future recruiters.
Evaluation and Reporting | 41 | 47 | Student | Be notified about Internships Submission Cycle | I can submit my report on time and avoid missing deadlines.
Evaluation and Reporting | 46 | 48 | Student | Tag other Students that worked with me in my post | the post can appear on their profile and acknowledge their contributions
Evaluation and Reporting | 39, 40 | 49 | SCAD | Review and approve/reject student internship reports | Students can receive timely feedback and make necessary corrections
Evaluation and Reporting | 39, 40, 49 | 50 | SCAD | Notify Students if their internship was rejected and the reason why | they can be prepared to reapply in the next submission cycle